School Improvement & Development Plan 2014-15

| Priority: | Key Objective | Key Ofsted Area(s): | Links to School Vision: |
| --- | --- | --- | --- |
| 1. | To develop Outstanding teaching practice across the school | Quality of Teaching & Learning | Love of Learning Make it Your Best Skills for Life |
| 2. | To embed High Quality feedback across the school | Quality of Teaching & Learning Pupil Achievement | Love of Learning Make it Your Best Persevere |
| 3. | To promote sustained rapid progress of all children including vulnerable groups in reading, writing and Maths | Quality of Teaching & Learning Pupil Achievement | Love of Learning Make it Your Best Persevere |
| 4. | To effectively implement the New National Curriculum requirements | Quality of Teaching & Learning Pupil Achievement Leadership and Management Behaviour and Safety | Skills for Life |
| 5. | To strengthen the school’s leadership capacity and sustainability | Leadership and Management | Love of Learning Make it Your Best |
| 6. | To strengthen the effectiveness of Governors | Leadership and Management | Love of Learning Make it Your Best |

* Termly Actions & detail found in TAP. (Termly Action Plans)

** Priorities 1,2 and 3 are linked.

*** Priorities 3 and 4 are partially linked.

| Priority: 1 |  | To develop Outstanding teaching practice across the school |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Monitoring in the last 2 cycles suggests that teaching is consistently good in each classroom, with some examples of outstanding practice. Monitoring includes termly exercise book scrutiny, analysis of achievement data and lesson observations. Peer observations occur each term. |  |  |  |  |  |
| Success Criteria |  | Majority of teaching graded outstanding, majority of progress measures indicate outstanding, all sub-groups progress well gaps (eg PP) narrow |  |  |  |  |  |
| Every Child Matters |  | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |  |  |  |  |  |
| Ofsted |  | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC |  |  |  |  |  |
| Vision |  | Love of Learning Make it Your Best Perseverance Skills for Life |  |  |  |  |  |
| Key Objective: |  | Embedding outstanding practice across school. (link priority 2&3) |  |  |  |  |  |
| Intended Outcomes | Actions |  | Who | Resource/Time | Timescale | (TAP) | Monitoring |
| 1. Teachers familiar with recent research into features of outstanding practice in schools in England | a. Staff meeting time in Summer time looking at higher level questioning and lesson study model b. Triad of teachers released for lesson study re: questioning |  | Head/ Teachers | Staff Meeting Time- Summer Term Supply for triad £1000 | Summer Term 2014 | Summer Term- TAP | Head checks actions and reports to FGB and at TAP review meetings |
| 2. Teachers reflective on and develop own practice | a. Lesson study model extended and a different foci chosen for each term b. ‘Learning for All’ policy written (to also include teaching non-negotiables) |  | Head/ Teachers | Staff Meeting Time- Summer Term & planned for future terms | Summer & Autumn Term 2014 | Summer & Autumn Term - TAP | Head checks actions and reports to FGB and at TAP review meetings |
| 3. Teaching and children’s learning and engagement graded Outstanding. | a. Teachers implement reflective practices in everyday teaching b. Progress measures outstanding in all areas; subgroups progress well; gaps close. (link priority 3) |  | Teachers |  | Ongoing and reviewed on a termly basis | Autumn Term TAP | Termly Pupil Achievement reports- to FGB and at TAP review meetings |
| Suggested Governor Monitoring Activities: Governor termly monitoring- talk to children and continue to focus on teaching non-negotiables |  |  |  |  |  |  |  |

| Priority: 2 |  | To embed High Quality feedback across the school |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Quality of feedback a key aspect of promoting rapid progress for children (link priority 1&3). In 2013 we reviewed and rewrote our Target and Feedback policy following work as a staff on AfL and Sutton Trust research. This has resulted in examples of excellent marking across the school. It is however an important ongoing priority, particularly around ensuring children respond to marking. |  |  |  |  |  |
| Success Criteria |  | Children regularly respond to marking within ‘learning dialogues’. The majority of children are actively and routinely engaged in their targets and in peer and self-assessment against success criteria. |  |  |  |  |  |
| Every Child Matters |  | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |  |  |  |  |  |
| Ofsted |  | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC |  |  |  |  |  |
| Vision |  | Love of Learning Make it Your Best Perseverance Skills for Life |  |  |  |  |  |
| Key Objective: |  | To embed High Quality feedback across the school (link priority 1&3) |  |  |  |  |  |
| Intended Outcomes | Actions |  | Who | Resource/Time | Timescale | (TAP) | Monitoring |
| 1. Establish Target and Feedback policy capturing best practice | a. Review latest Target and Feedback policy in light of experience from last year and amend where needed. b. Time set aside in classes for responding to marking |  | Head/Teachers | Staff Meeting Time- Summer Term | Summer Term 2014 | Summer Term TAP | Head checks actions and reports to FGB and at TAP review meetings |
| 2. High quality feedback and children’s responses common in exercise books | a. Continue to monitor regularly and actively promote children’s responses. |  | Head/Teachers | HT and key subject leaders time | Ongoing- at least termly task |  | Head checks actions and reports to FGB and at TAP review meetings |
| Suggested Governor Monitoring Activities: Look at books during monitoring visits. Are children responding to marking? Are there learning dialogues? |  |  |  |  |  |  |  |

| Priority: 3 |  | To promote sustained rapid progress of all children including vulnerable groups in reading, writing and Maths |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Termly achievement data has continued to rise since December ’12 baseline. End of Key Stage projections for 2014 and 2015 look good. This progress needs to continue across the school (link priority 1) |  |  |  |  |  |
| Success Criteria |  | Termly achievement data analysis hits global targets: KS2 100% on target for 2 levels 1.2average pts/term progress KS1 100% on target for 6 sub-levels across key stage 2.2 average pts/term progress |  |  |  |  |  |
| Every Child Matters |  | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |  |  |  |  |  |
| Ofsted |  | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC |  |  |  |  |  |
| Vision |  | Love of Learning Make it Your Best Perseverance Skills for Life |  |  |  |  |  |
| Key Objective: |  | To promote sustained rapid progress of all children including vulnerable groups in reading, writing, Maths (link priority 1&2) |  |  |  |  |  |
| Intended Outcomes | Actions |  | Who | Resource/Time | Timescale | (TAP) | Monitoring |
| 1. Children to make sustained rapid progress in Mathematics. | a. Further broaden range of Wave2/3 Maths interventions available to school. b. Introduce Big Maths weekly sessions in Autumn Term c. Review curriculum to establish and plan regular cross-curricular & real life Maths opportunities |  | Teaching Assistants Teachers | Catch Up Numeracy training £800 Big Maths training £400 | Summer Term 2014 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 | Head checks actions and reports to FGB and at TAP review meetings Termly Achievement Reports |
| 2. Children to make sustained rapid progress in Writing. | a. Review and refine effectiveness of Big Writing introduction in Sept’13 b. Clearly plan cross-curricular extended writing opportunities- link to priority 4 c. Review spelling progress data and organisation of groups within the school d. Training organised on SP&G, inc KS1 |  | Teachers HT | Training £300 Staff meeting time | Summer Term 2014 Autumn Term 2014 | TAP Summer’14 TAP Autumn ‘14 | Head checks actions and reports to FGB and at TAP review meetings Termly Achievement Reports |
| 3. Children to make sustained rapid progress in Reading. | a. Review texts used across the curriculum- link priority 4 b. Conduct library audit & restock c. Library renovation project- link to Premises Development |  | Teachers HT | Staff meeting time Books & Audit £500 Capital funding £20k | Across 2014-15 SIDP | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 | Head checks actions and reports to FGB and at TAP review meetings |
| Suggested Governor Monitoring Activities: Discuss with Teaching staff & HT during termly TAP review meetings |  |  |  |  |  |  |  |

| Priority:4 |  | To effectively implement the New National Curriculum requirements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Statutory requirement for September 2014. Identified need to reform SEAL curriculum for needs of children in LMPS. |  |  |  |  |  |
| Success Criteria |  | Statutory requirements are met, and school retains existing strengths in its cross-curricular approach Assessment arrangements are in |  |  |  |  |  |
| Every Child Matters |  | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |  |  |  |  |  |
| Ofsted |  | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC |  |  |  |  |  |
| Vision |  | Love of Learning Make it Your Best Perseverance Skills for Life |  |  |  |  |  |
| Key Objective: |  | To implement the new statutory curriculum |  |  |  |  |  |
| Intended Outcomes | Actions |  | Who | Resource/Time | Timescale | (TAP) | Monitoring |
| 1. Curriculum changes identified and reflected on | a. Teachers familiarise themselves with new curriculum b. Teachers identify key areas for development in subject audits |  | Teachers | NIEAS Briefings Cluster network 2013-15 Subject audits (Spring ’14) | (From Sept’13) Spring & Summer 2014 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 | HT checks actions and reports to FGB |
| 2. Teachers plan for new curriculum and introduce provisional elements | a. New curriculum overview planning completed each term in advance- trial elements in summer term 2014 b. Teachers aware of expectations in relation to year groups (supported by cluster network groups) c. Cross curricular links established (link priority 3) |  | Teachers | Staff meeting time | Spring 2014 inset day Summer 2014 inset day | TAP Summer’14 TAP Autumn ‘14 | HT checks actions and reports to FGB |
| 3. Curriculum coverage ensured | a. Curriculum-specific resources audited, investigated and purchased. |  | Subject leaders | Curriculum resources - £2000 est | Summer Term ’14, but new resource needs will be ongoing | TAP Summer’14 | HT checks actions and reports to FGB |
| 4. Establish outstanding pupil attitudes towards safety & SMSC | a. Plan new cross-curricular topic ‘staying safe and healthy’ to incorporate range of areas b. Review assembly themes and establish consistent high quality approach to assemblies |  | Teachers HT | Staff meeting time Assembly training £500 | Summer Term ’14 for planning of new topic Autumn Term 2014 for focus on assemblies | TAP Summer’14 TAP Autumn ‘14 | HT checks actions and reports to FGB |
| Suggested Governor Monitoring Activities: Discuss with Teaching staff & HT during termly TAP review meetings |  |  |  |  |  |  |  |

| Priority: 5 |  | To strengthen the school’s leadership capacity and sustainability |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Middle leadership role growing and clearly defined in school’s ‘Development Planning Cycle’. Good quality annual subject audits and reporting to governors within termly TAP meetings. Small schools recommended/advised to investigate collaboration, partnership or federation with similar schools by Local Authority. No other senior leaders in school apart from HT. Good and Outstanding schools should demonstrate how they work collaboratively with other schools (Ofsted) |  |  |  |  |  |
| Success Criteria |  | Leadership links developed with other schools |  |  |  |  |  |
| Every Child Matters |  | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |  |  |  |  |  |
| Ofsted |  | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC |  |  |  |  |  |
| Vision |  | Love of Learning Make it Your Best Perseverance Skills for Life |  |  |  |  |  |
| Key Objective: |  | Outstanding Leadership & Management |  |  |  |  |  |
| Intended Outcomes | Actions |  | Who | Resource/Time | Timescale | (TAP) | Monitoring |
| 1. School positioned within triad ‘hub’ of 2 other similar schools in mutually beneficial relationship | a. HT to have meetings with other similar schools to establish a hub model. b. Hub model to include termly meeting to share data, SEF, SIDP/TAP, budgetary analysis, and possible shared practice or staff in time |  | HT | 1 day/term HT out of school | December ‘14 (post-Ofsted) | Autumn ‘14 Spring ‘15 |  |
| 2. Leadership practice of HT developed further through N2GG & London Leadership challenge | a. Membership of N2GG has provided good links and support- HT to continue to develop and make use of those networking links b. Head of N2GG has recommended HT to London Leadership challenge project next year |  | HT | N2GG £1000 pa 2 days HT out of school to participate in London Leadership challenge | Throughout SIDP 2014-15 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 |  |
| 3. Middle leadership continues to develop with clearly defined roles within school development structure | a. Continued investment in middle leadership, and delegated responsibilities within clear structure b. Opportunities made for middle leadership to visit other schools- link to hub model |  | HT Middle leaders | Training £500 Supply £500 | Throughout SIDP 2014-15 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 |  |
| 4. School continues to take opportunities to give receive support to other schools | a. Ongoing focus- many examples already b. HT will record in a section within SEF |  | HT Teachers | HT time to cover teachers for release | Throughout SIDP 2014-15 | TAP Summer’14 TAP Autumn ‘14 |  |
| Suggested Governor Monitoring Activities: Discuss with Teaching staff & HT during termly TAP review meetings. FGB meetings. |  |  |  |  |  |  |  |

| Priority: 6 |  | To strengthen the effectiveness of Governors |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Governor self-evaluation (Jan’14) and action plan (March ‘14) identified strengths and areas for further development. |  |  |  |  |  |
| Success Criteria |  | Governing body is highly effective in carrying out its monitoring role. |  |  |  |  |  |
| Every Child Matters |  | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |  |  |  |  |  |
| Ofsted |  | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC |  |  |  |  |  |
| Vision |  | Love of Learning Make it Your Best Perseverance Skills for Life |  |  |  |  |  |
| Key Objective: |  | To strengthen the effectiveness of Governors |  |  |  |  |  |
| Intended Outcomes | Actions |  | Who | Resource/Time | Timescale | (TAP) | Monitoring |
| 1. Governors monitoring effectiveness is outstanding | a. Chair and Vice Chair to attend all TAP review meetings and challenge staff. b. All governors to conduct a monitoring visit each term. c. Governors with a specific role to attend meeting with HT/staff responsible at least twice per year |  | Governors (incl Chair and Vice Chair) | Ongoing | Throughout SIDP 2014-15 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 | Chair of Governors |
| 2. Deepen and broaden Governors knowledge of school performance data | a. Govs to review Pupil asset data and termly Pupil Achievement report produced by HT b. Govs to undergo Governor services training in school performance data c. Govs to be aware of changes to school data under new National Curriculum |  | Governors | Ongoing New data systems for National Curriculum will emerge from summer ‘14 | Throughout SIDP 2014-15 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 | Chair of Governors |
| 3. To ensure that Governors communicate well with stakeholders and recruit new members succesfully | a. Govs to have a high pofile at well attended school events b. Chair to continue to write fortnightly for the school newsletter c. Advertising for governor vacancies o be reviewed and extended- parish magazines |  | Governors | Ongoing | Throughout SIDP 2014-15 | TAP Summer’14 TAP Autumn ‘14 TAP Spring ‘15 | Chair of Governors |
| Suggested Governor Monitoring Activities: Chair of Governors will report to FGM on progress. For more detail see Governor Action Plan (March ’14) |  |  |  |  |  |  |  |