School Improvement & Development Plan 2015-16

| Priority: | Key Objective | Success Criteria: | Key Ofsted Area(s): | Links to School Vision: |
| --- | --- | --- | --- | --- |
| 1. | To develop ‘Outstanding’ teaching practice across the school | All key Pupil Achievement data indicators* ≥ National QoT indicators reflect characteristics of Ofsted Outstanding for T,L&A | Quality of Teaching & Learning | Love of Learning Make it Your Best Skills for Life |
| 2. | To further raise achievement at KS2 | KS2 VA ≥ 100 every year in Maths, Reading and Writing and shows positive trends % children making expected and more than expected progress at KS2 ≥ National | Pupil Achievement | Love of Learning Make it Your Best Skills for Life Persevere |
| 3. | To further raise achievement in EYFS (start of 2 year plan) | GLD attainment ≥ National and/or % children making ‘typical’ progress ≥ 90% and % making ‘rapid’ progress ≥ National | Quality of Early Years Provision | Love of Learning Make it Your Best Skills for Life |
| 4. | To develop ‘Outstanding’ provision for High Ability and Gifted and Talented children | % Children L3 PA at KS1 making more than expected progress ≥ national Log of enrichment activities reflect high quality opportunities outside classroom | Leadership and Management | Love of Learning Make it Your Best |

* Defined as: GLD (Rec), Phonics Screening (Y1), KS1 SATS (Y2) & KS2 SATS (Y6)

Termly Actions & detail found in TAP. (Termly Action Plans) & GANT chart

Item 2 is linked to the strategic objectives of the Premises Development plan

Item 3 has been identified from Sept’14 as a key area. Further investment and planning will be over a 2 year cycle.

| Priority: 1 | To develop Outstanding teaching practice across the school |
| --- | --- |
| Rationale | Monitoring in the last 6 cycles suggests that teaching is consistently good in each classroom, with some examples of outstanding practice. Monitoring includes termly exercise book scrutiny, analysis of achievement data and lesson observations. Teachers are reflective and committed to own professional development linked to educational research. |
| Success Criteria | All key Pupil Achievement data indicators* ≥ National. Majority of teaching graded outstanding, majority of progress measures indicate good or outstanding, all sub-groups progress well gaps (eg PP) narrow. Self-evaluations of teaching demonstrate reflection and positive trend. |
| Every Child Matters | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |
| Ofsted | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC Early Years |
| Vision | Love of Learning Make it Your Best Perseverance Skills for Life |
| Key Objective: | Embedding reflection and outstanding practice across school. |
| Intended Outcomes | Actions | Who | Resource/Time | Key Milestones | Termly Action Plan | Monitoring & Evaluation |
| To understand key factors identified through research as linked to highly effective teaching. To develop a continuous self-evaluation and review of performance in order to develop and refine highly effective teaching. | Summer term staff meeting time to discuss and evaluate Durham University (Oct’14) synthesis of all underpinning research. Create a list of criteria from this and Hattie (‘Visible learning 2011) linked to our teaching non-negotiables, which teachers will grade themselves on a scale of 1-5. Teachers (&HLTAs) to set themselves objectives for the next term based around improving their score in one of these. Results included as part of the established termly ‘teaching and learning cycle. | All teaching staff | Staff meeting time | Half-term May’15 Completed all discussion of research and findings and given staff the self-evaluations End of each term Latest self-evaluations completed and actions taken. | Actions indicated frontloaded for summer term, but them absorbed as part of termly cycles | Mar’16 Final evaluation SEFs completed..monitoring suggests some examples of refinements to practice- see T&L evaluations Pupil achievement data (latest-Mar’16) (2016 projections) are positive and could hit sc indicated. |
| To (further) develop reflection on own teaching performance through visiting other schools and developing professional network * | Continue to active pursue opportunities for staff (including TA’s) to visit other schools and also to support others including through professional networks and activities facilitated by ‘Norfolk Better to Best’ membership | All teaching staff | EYFS,Maths, Literacy network 3x£750 (NIEAS) N2BB- £2,500 HT to cover teacher visits where possible | This is ongoing- the impact of visits is discussed termly as part of ‘Teaching and Learning evaluations’. | Details of planned future visits will be included on TAP and record in CPD log. | Mar’16 update Good progress and evidence of impact..links ongoing-see Governor monitoring (Mar’16) |
| To (further) use the termly ‘Teaching and learning evaluation’ structure to identify key gaps in subject knowledge for CPD * | Continue to use termly structure. CPD booked on basis of these identified gaps. | All teaching staff and Teaching Assistants | £2000 est | See above | Details of planned future CPD will be included on TAP and record in CPD log. | Mar’16 update Good progress- evidence of teachers involved in driving individual PD |
| Suggested Governor Monitoring Activities: Teacher interviews and discussion of self-evaluation documents |

* These are a continuation of a key strategy for developing Quality of Teaching over time.  Reiterated here to signify importance.

| Priority: 2 | To further raise achievement at KS2 |
| --- | --- |
| Rationale | Reading data suggests outstanding attainment at KS1, and high parental support. KS2 progress data is also at national levels (aggregated over the last 3 years), but could be improved towards outstanding. Current small library in thoroughfare of school is barely fit for purpose, either as library or learning space. Accelerated Reader ties in with our online Junior Librarian system and is designed to promote independence KS2. |
| Success Criteria | Reading data at both KS2 and KS1 is at or above national indicators. Pupil and parental voice and monitoring indicates increased reading. |
| Every Child Matters | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |
| Ofsted | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC Early Years |
| Vision | Love of Learning Make it Your Best Perseverance Skills for Life |
| Key Objective: | Promote independence and reading for pleasure, particularly at KS2. |
| Intended Outcomes | Actions | Who | Resource/Time | Key Milestones | Termly Action Plan | Monitoring & Evaluation |
| To create a new library room to enable children to have an additional quiet space for working and to learn independent library skills and promote love of reading, and to allow 5 classes. | Building project targeted for Autumn 2015. Follow up actions in moving resources and creating environment ideally by Christmas 2015. (see also Premises Development plan for progress of this long standing strategic aim). | Outside contractors, project managed by NPS. | £70,000 est (latest quote £66,500 with potential to reduce by £4k on ceiling- awaiting confirmation with tree issue) | December ‘15 Building completion aim. April ‘16 Library in operation, plus used as additional teaching space. Costed f/t teacher for financial year 2016-17 | This will not be included in TAPs because it is project managed by external agents. | Mar’16 update Build scheduled for completion by Sept’16. Library service have visited to advise on layout and possible; resources. |
| To expand the available stock in the library and introduce the Accelerated Reader program to promote independence of children in choosing and reading. | Dependent on timeline above, AR program to be introduced once new room complete. New stock to be added from gaps identified in Library audit | HT & English Subject Leader | £1,935 (1st year) New Stock £2,000 + fundraising from Friends | July ‘15 Decisions made re: stock and set up of Accelerated Reader. Sept’15 AR introduced and used by children Apr ‘16 Budget decisions re: further stock | This will be included in TAP planning following further research (scheduled visit to Horsford Jnr School in March) | Mar’16 update Most books catalogued and all training completed. Gaps in stock identified- mainly at extreme ends of catalogue. Planned parent meeting/info evening next h/t |
| To use existing staff to appoint a p/t librarian to manage AR and library stock | Dependent on timeline above, budget for weekly p/t hours to work in library- could include delivery of library skills sessions to children. | HT & staffing governors | £1,500est (based on additional 3 hrs/week from Jan’15) | Sept’15 Cost for setting up AR and introducing with children Jan 16 Migration of books to new library | Spring 2016 TAP, or sooner dependent on above timelines. | Mar’16 update In budget from April’16. Reading data (Mar’16) is strong across the school and projected results are good- see termly data analysis. |
| Suggested Governor Monitoring Activities: Premises committee will monitor progress of building project. Once complete, library development will be the subject of future monitoring tasks by selected governors eg pupil choice and observations of library skills sessions, use of AR scheme in promoting independent readers at KS2 |
| Priority: 3 | To further raise achievement in EYFS |
| Rationale | EYFS achievement data is ‘good’, but aim is to secure outstanding provision. New staff team (from Sept’14) and historic underinvestment in provision make this apposite time for fresh investment. Succession planning and staff appraisal objectives also indicate the desirability for the school of broadening EYFS specialist knowledge across more teaching staff to promote securer future succession and collaboration to secure best outcomes for children. |
| Success Criteria | EYFS data and other QoT indicators suggest securely good with outstanding elements. EYFS knowledge is diffused across KS1 and leadership. |
| Every Child Matters | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |
| Ofsted | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC EYFS |
| Vision | Love of Learning Make it Your Best Perseverance Skills for Life |
| Key Objective: | To further raise % of children achieving a GLD, and % making ‘rapid’ progress from baseline |
| Intended Outcomes | Actions | Who | Resource/Time | Key Milestones | Termly Action Plan | Monitoring & Evaluation |
| To use a holistic approach to further raise the quality of EYFS provision | Complete a thorough EYFS SEF in the summer term (from Anna Ephgrave ‘Outstanding EYFS’) with all relevant staff and governors. Use the completed SEF to create a 2-year Action plan in Gantt chart form to highlight key actions. Drive action plan through over next 2 academic years. (Could link to future new outdoor area off new classroom). | HT, BC, KP and EYFS Governor(s) | Identify spending once completed SEF. Estimated figure of £10,000 over 2 year period- speed dependent upon cost of premises redevelopment (see Priority 1 above) Release time for SEF- £200 | By July’15 EYFS SEF & Action Plan (summer term’15) Two year development plan drafted and shared with stakeholders | Summer term TAP will identify actions indicated. Autumn and Spring term TAP plans will be driven by outcomes of SEF. | Mar’16 update All actions completed. Improvement plan of 4 areas identified. Progress of children in 2015 cohort has been good in specific and rapid in prime. Investment ongoing- current focus outside & sensory room. |
| To broaden the base of EYFS staff specialism within the school (teachers and teaching assistants) | Continue to invest in CPD opportunities and networking visits for BC, KP and AP to develop further EYFS knowledge (this is linked to Priority 1 of the SIDP and also to appraisal objectives). Create some opportunities for other staff indicated to teach EYFS for periods of school week to develop expertise. Encourage Governor training in EYFS, to broaden further expertise in monitoring. | HT, BC, KP and EYFS Governor(s) | Costs will be drawn from the training budget indicated in Priority 1- focus also on TA’s in EYFS. HT will continue to release staff by covering their classes for visits to other schools and training. | Ongoing strategy- decisions re: training and visits. Could also influence decision re: potential recruitment of p/t Y1 teacher in April’16 | Details of planned future visits will be included on TAP and record in CPD log. | Mar’16 update All actions completed. See above. Teacher led and PD opportunities for staff have happened and impact described in interviews with staff. |
| To utilise and evaluate an EYFS baseline assessment from Sept’15 which provides valuable formative assessment for teachers. | Baseline tests ordered (Summer ’15) and trialled (Sept’15). Discussions- Autumn Term 2015 re: which to select and use from statutory requirements in Sept’16. | HT and BC | Staff meeting time Training provided through EYFS network (see above) | By July’15 Decision finalised re: assessment model. Sept’15 First use. Apr’16 Review re Sept’16 | Summer term and Autumn term TAP will identify actions indicated. | Mar’16 update All actions completed. Baseline to be discussed in light of national u-turn. |
| Suggested Governor Monitoring Activities: Teacher interviews and pupil voice. Visits to EYFS session and setting. |
| Priority:4 | To develop outstanding provision for High Ability and Gifted and Talented children |
| Rationale | Work on higher level questioning and G&T register (updated termly) and provision is a solid foundation for further development of this area of the schools work. Data (both internal and external) suggests that whilst HAP children achieve well, lesson monitoring sometimes indicates that an even higher degree of challenge could be provided. |
| Success Criteria | Data suggests that HAP children make rapid progress. Enrichment information (G&T register of actions) shows thorough and varied opportunities- including some in school intervention. |
| Every Child Matters | Be Healthy Enjoy & Achieve Stay Safe Make a Positive contribution Achieve economic wellbeing |
| Ofsted | Pupil Achievement Quality of Teaching Behaviour & Safety Leadership & Management SMSC EYFS |
| Vision | Love of Learning Make it Your Best Perseverance Skills for Life |
| Key Objective: | To further increase achievement and enrichment opportunities for HAPs |
| Intended Outcomes | Actions | Who | Resource/Time | Key Milestones | Termly Action Plan | Monitoring & Evaluation |
| To develop outstanding provision for G&T and HAP children | Evaluate strengths and weaknesses of our current provision and look at best practice nationally from case studies in order to formulate action plan. Staff meeting time to discuss Sutton Trust recommendations (2012 report) (link to SIDP 1) | All teaching staff | Staff meeting time and possible release time for drafting action plan £100 (0.5 release day) | By July’15 Summer term ’15 for initial evaluation and action planning Action plan will detail further. Sept’15 Action plan start. | Summer term TAP will identify actions indicated. Autumn and Spring term TAP plans will be driven by outcomes of evaluation and discussion. | Mar’16 update All actions completed. Data re: HAP children is good, and provision has been improved. |
| To facilitate enhanced role for G&T co-ordinator to further improve outcomes for G&T and HAP children. | Protected time for G&T co-ordinator to work with children and organise activities/monitor Organise visits to other schools with outstanding provision Use Cluster support worker for Inset opportunities Membership of Norfolk Children’s University | HB AP | Use HT cover to release co-ordinator to implement action plan. If budget allows could instead or in addition pay 0.5 day per half-term for teacher to have non-contact to do this £600 Children’s University £? (not on STS site) | See above. | Autumn TAP 2015 will detail structure | Mar’16 update All actions completed- ‘Childrens University’ moved to 2016-17 SIDP as part of proposed curriculum and enrichment focus for next year.- |
| Suggested Governor Monitoring Activities: Discuss with Teaching staff & HT during termly TAP review meetings |