Termly Action Plan (TAP)- Autumn Term 2016 (September-December 2016)

(Key actions drawn from SIDP & shared with staff. Governors included in termly planning, monitoring and review meetings.)

| Priority: | Key Objective: | Success Criteria: | Ofsted Area: |
| --- | --- | --- | --- |
| 1. | To increase the percentages of children making ‘rapid’ progress in Maths and English | - % of children achieving ‘high score’ in end of KS2 tests > national in 2017 - VA measure for school is significantly > national average at KS2 in 2017 - FFT progress measure is in top 25% schools at KS1 in 2017 - EYFS proportions making ‘rapid’ progress is >40% in 2017 | Outcomes for Pupils |
| 2. | To further develop an outstanding and extended curriculum | - Pupil Outcomes reach the criteria listed in Priority 1. - Curriculum planning shows exciting learning opportunities across all subjects and with a good breadth of extra-curricular opportunities including ‘Children’s University’ - Teaching strategies are appropriately linked to our ‘Teaching non-negotiables’ underpinned by NCETM/UKLA guidance - Tracking of foundation subjects shows that at least 40% of children are achieving above age expectations in each subject area - Pupil and parent voice indicates high levels of satisfaction with curriculum experiences for children | Outcomes for Pupils Quality of Teaching, Learning and Assessment |
| 3. | To develop outstanding provision in ICT | - Computing curriculum develops and extends all aspects of the National curriculum 2014 - All objectives identified in the ICT curriculum SEF have been met | Quality of Teaching, Learning and Assessment |
| 4. | To develop the most effective tracking system towards end of Key Stage outcomes | - Management: Tracking is predictive of key stage outcomes, accurately identifying children in need of additional support to reach national expectations. It includes information from across foundation subjects. - Teaching: Assessment informs and shapes future teaching sequences by identifying gaps in learning, is flexible, is time-effective’ is age-appropriate and does not add unnecessarily to workload. | Quality of Teaching, Learning and Assessment Effectiveness of Leadership & Management Outcomes |
| 5. | To achieve the Linguamarque’ award for FL | - Linguamarque accreditation has been awarded to school. - FL curriculum has outstanding features. | Quality of Teaching, Learning and Assessment |

| Target: | Input, activities & tasks (Including key ‘milestones’) | Resources | Person | Monitoring | Success Criteria | Evaluation (for data outcomes see termly WS summary and analysis for next TAP) | Evidence (for data evidence see termly WS summary and analysis for next TAP) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SIDP PRIORITY 1 To increase the percentages of children making ‘rapid’ progress in Maths and English | Mastery Learning - Release time for subject lead to develop timeline for ‘mastery learning approach’ (14.9.16) - Staff meeting (led by SC) to introduce approach Professional Networks - Cluster and NIEAS groups attended-see diary. Termly Teaching Evaluations - Cycle 12 with external HT (Sept’16) HT Ludham Actions from Subject Audits (English & Maths) - Review spellzoo - Measure impact of AR across school - Update Calculation Policy - Embed Maths Meetings Y1-4 | Release time for subject leader (2xpm £150) EYFS network Maths network Literacy network £450 N2BB £1900 HT to cover teacher visits where possible | SC BC SC KP AP KP SC | AP Two identified Governors FGM (19.4.16) | All staff have applied mastery and collaborative learning approaches. (Evidence from cycle 12 monitoring) Feedback on impact of network meetings is good. (Evidence from termly teaching & learning eval.) | All actions completed. Release time and subsequent staff meeting completed. SC showed staff a variety of applications and some practical resources. Also now Cluster Lead. Audit of curriculum time and KS2 SATS analysis complete for both M and R. AR trial home access to Y2 children. AR now embedded across school and library usage much improved following new build and more hours for librarian. Next steps- to pick up in next book scrutiny of Maths. Embed Maths Meetings. | Subject Leader records. Termly teaching & learning evaluations- monitoring file. Cluster Maths Development Plan. Governor Monitoring (12.12.16) |
| SIDP PRIORITY 2 To further develop an outstanding and extended curriculum | Children’s University - Display board in school- October’16 to celebrate achievements - See CU timeline of actions Curriculum Review - UKLA English and NCETM Maths self-evaluation tools>results and key priorities disseminated to staff 21.9.16 staff meeting | PP money as funding for subsidising CU activities £750 | KA All | Two identified Governors FGM (19.4.16) | There is at least 85% of children uptake of some Children’s University activity by end of summer term. | All actions completed. CU board details considerable uptake and activity across school. Next steps- external clubs into school, more support for Disadvantaged children, graduation. Curriculum reviews completed and staff meeting held. Next steps- to pick up in next book scrutiny and look at the themes that emerged. |  |
| SIDP PRIORITY 3 To develop outstanding provision in ICT | NAACE Self-Review Toolkit - Write final action plan (Sept’16) - Evaluate impact of new broadband speed. - Staff meeting skills audit (28.9.16)> identify PD requirements for Autumn/Spring TAP - Finalise dates for visit to Hempnall Primary to evaluate Chromebooks & supporting software | NAACE £50 ICT resources £4,000 | AP | RC Governor | Key areas identified and a timeline and action plan is clear. Decision made re: hardware investment | All actions completed. Staff Meeting held 7.12.16 Good consensus around areas to move forward on. New ICT lead (BC) to create a timeline of next steps for new year. | Computing Action Plan- updated (Dec’16) Staff Meeting minutes 7.12.16 |
| SIDP PRIORITY 4 To develop the most effective tracking system towards end of Key Stage outcomes | Post SAT review - Collate data from different known schools- compare with test outcomes for KS2 M/R/GPS> use to review effectiveness of our tests as a predictive tool (Sept’16) KS1 Assessment review - Trial use of Accelerated Reader as support for TA in Reading SEND Assessment - Evaluate use of Blue Square materials- staff meeting (SC led) (2.11.16) | £500 possible Scholastic or Testbase end of Year tests Blue Square has been cluster funded | AP KP | Two identified Governors FGM (19.4.16) | Analysis of efficacy of tests as predicitive tool is clear. KS1 and SEND children assessment is tracked more accurately. | All actions completed except Blue Square SEND. Our predictions were very close to the actual outcomes except where very high challenge threshold of Reading SATS was a surprise. AP has contacted both PIRA and AM and got their data and also from two other schools. Some tentative conclusions have been made re: predicted grades- but have also decided (in light of high challenge of Reading) to look at Twinjke test too and trial for this term. | PIRA and AM charts. Raw data from two schools. WS achievement predictions (Sept’15 vs June ’16) |
| SIDP PRIORITY 5 To achieve the Linguamarque’ award for FL | Linguamarque/FL development - KS2 introduction of Languages portfolio for evidence and assessment - Y3/4 begin French following new scheme of work - Application for International Schools Award Accreditation - Formal observation by Marina Dixon for Linguamarque Bronze accreditation> action plan to achieve silver accreditation | £300 Linguamarque £500 CPD FL (eg Conference & training) | JH | AP Two identified Governors FGM (19.4.16) | Key areas identified and a timeline and action plan is clear. | All actions completed. Bronze linguamarque achieved. Timeline and actions started for Silver. Very positive developing area of school curriculum. | Subject leader file. EDP story |

Gantt Chart- Autumn Term

Tasks

| w/b | 5.9.16 | 12.9.16 | 19.9.19 | 26.9.16 | 3.10.16 | 10.10.16 | 17.10.16 | Half-term | 31.10.16 | 7.11.16 | 14.11.16 | 21.11.16 | 28.11.16 | 5.12.16 | 12.12.16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Whole School cycles: | Pupil Progress meetings SEND/PP reviews | Target setting- end of Year Outcomes Curriculum maps |  | EYFS baseline completed |  | Teacher Appraisal meetings | Attndance analysis-1 |  | Sports Premium review meeting |  | TA Performance Management interim review meetings | HT Appraisal Meeting | Assessment week Attendance analysis-2 | SEND/PP reviews Pupil Voice survey | TAP review Termly Pupil Achievement Data |
| SIDP 1: Quality of Teaching |  | SC release time for staff meeting prep(am) | SC Maths Mastery staff meeting | External obs- Ludham HT |  |  | AP Collbrative learning staff meeting |  |  |  |  |  |  |  |  |
| SIDP2: Curriculum |  | SC/KP staff meeting re: maths and English reviews |  | CU display board & assembly |  |  |  |  |  |  |  |  |  |  | CU review |
| SIDP 3: ICT |  |  |  | AP ICT skills audit & draft action plan & review of new broadband | AP Finalise action plan |  |  |  |  |  |  |  |  |  |  |
| SIDP 4: Assessment |  |  | AP Data collection & analysis |  |  |  |  |  | Blue Square staff meeting |  |  |  |  |  |  |
| SIDP 5: Foreign Languages |  | KS2 portfolios start |  |  | M.Dixon obs visit |  |  |  | Action plan for silver |  |  |  |  |  | MFL plan review |