Termly Action Plan (TAP)- Summer Term 2017 (April-July 2017)-COMPLETED

(Key actions drawn from SIDP & shared with staff. Governors included in termly planning, monitoring and review meetings.)

| Priority: | Key Objective: | Success Criteria: | Ofsted Area: | Links to School Vision: |
| --- | --- | --- | --- | --- |
| 1 | Teaching & Learning To further improve rates of progress across all key stages in the school. | Key themes from EEF Foundation Toolkit have been discussed, selected, applied and embedded into school practice. This contributes to: - FFT VA progress scores place school in ‘Top 20’ for KS1 and KS2 - KS2 VA is >national for reading, writing and maths - RAISEOnline progress matrix for EYFS>KS1 shows that proportions of all groups and sub-groups make progress at or above national - Proportions of children making at least 5 sub-levels of progress across the Foundation stage in Specific Areas of Learning are >40% | Quality of Leadership & Management Quality of Teaching, Learning & Assessment Outcomes for Pupils Early Years | Love of Learning Persevere Skills for Life |
| 2 | Teaching & Learning To specifically improve the rate of progress for less able children at KS1 | A robust range of interventions for less able learners at KS1 is in place and being used so that: - Proportions who did not reach ELG at end of Foundation stage but subsequently reach ‘Expected standard’ at end of KS1>national in Maths and English - A higher than current proportion of children who do not reach ELG in Reading do go on to achieve Phonics Screening check at end of Year 1 (>national) | Outcomes for Pupils Quality of Teaching, Learning & Assessment | Love of Learning Persevere |
| 3 | Teaching & Learning To further develop curriculum focussed Interventions for Maths across KS2 | Rigorous analysis of gaps in learning from test data- both at end of KS2 SATS and in termly ‘Assertive Mentoring’ tests leads to (i) curriculum review (ii) specific small group time-limited intervention so that: - FFT VA Maths progress scores place school in ‘Top 20’ for KS2 - KS2 VA is >national for Mathematics | Quality of Leadership & Management Quality of Teaching, Learning & Assessment Outcomes for Pupils | Love of Learning Persevere |
| 4 | Curriculum To further develop outstanding provision in computing (building on SIDP 16/17) | Technology is reliably supporting and extending learning across the curriculum. - Teacher subject knowledge is highly secure. - Pupil voice is highly positive. - Home learning in ICT supports and extends tasks in school. | Quality of Teaching, Learning & Assessment | Love of Learning Persevere Make it your Best Skills for Life |
| 5 | Foundation Subjects To further develop high quality outcomes and assessment in foundation subjects | Attainment in foundation subjects is tracked in more detail so that - Termly whole school data report sheets are highly accurate. - Assessment provides useful information to inform teaching sequences and curriculum provision | Quality of Teaching, Learning & Assessment Leadership & Management | Love of Learning Skills for Life |

| Target: | Input, activities & tasks (Including key ‘milestones’) | Resources | Person | Monitoring | Success Criteria | Evaluation (for data outcomes see termly WS summary and analysis for next TAP) | Evidence (for data evidence see termly WS summary and analysis for next TAP) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Teaching & Learning To further improve rates of progress across all key stages in the school. | EEF Toolkit Review By end of Summer Term Initial staff meeting sessions- supported also be video extracts of Hattie rationale behind ‘Visual Learning’ (nb statistical weaknesses of Hattie conclusions- but a good articulation of the concept) Follow up session looking in more detail at top dozen potentially applicable approaches- selection of 2 themes by teaching staff to take forward. These will become focus. HT to identify training opportunities and/or resources required to introduce, review, embed and monitor the selected themes. Timeline created to encapsulate above- including resources required. By end of Summer Term- (from core subject audits) Maths - To update maths policy to incorporate ‘mastery’ and ‘mindset’ philosophies. - To embed updated calculation policy and share with parents through ‘café’ style events. English - Embed Accelerated Reader further and look at ways to use Early Literacy to support pre-Accelerated Reader children. - Research further approaches to teach and improve spelling. EYFS - To provide greater opportunities for CAL in the outdoor environments e.g. small world tyres, dinosaurs, fairy garden - Key Person Requirements of EYFS need to be clearer - (for new intake) - Future visits from parents within the daily classroom environment where T or TA can sit with parent 1:1 or in a small group to support/guide with areas of challenge at home, or areas where the child needs further development e.g. reading | 2 staff meetings Training as required Release time to write policy (PGCE support) Subject leader time Friends and school fund money (£500) Next ‘stay and play’ morning | AP SC KL BC | Standards SC LP | Key themes from EEF, with reference to Hattie have been discussed, selected, applied and embedded into school practice. Maths policy reflects practice. Calculations policy has been shared with parents and reflects practice. Early Literacy function is supporting emergent readers Outdoor environment has been further developed making use of summer term weather Key Person strategy has been adapted for Sept’17 | EEF objectives- collaborative learning chosen + one other – inset 4.9.17. Will then inform appraisal training requirements 10.17. Maths policy draft complete- full review at Standards SC in October. Cluster have made progress with a curriculum map and calculations policy- to be finalised at next Maths hub and shared with parents by Dec’17. School is using White Rose as basis for most Maths planning- and new cluster work will reflect that. English draft complete- full review at Standards SC in October. EYFS actions complete. | Staff meeting notes. Draft policies EFYS plans |
| Teaching & Learning To specifically improve the rate of progress for less able children at KS1 | By end of summer term Extend and embed use of First Class @ Number- into Y1/2 - JT to refresh VM and run a group in second half of summer term Review, through a skills audit, the other range of interventions we can currently offer, and research any that might be beneficial eg WriteAwayTogether Reading Recovery Catch Up Reading Numbers Count Ref: DfE ‘Literacy and Numeracy Catch-Up Strategies’ (11/12) Advertise and appoint KS1 TA job share to lead interventions for targeted group- once have decided exactly which interventions looking for | Subject leader time to research interventions AP/Governors (inc KL) | KL/JT KL/AP | Standards SC JM | A robust range of interventions for less able learners at KS1 is in place and being used. Proportions of children who did not reach ELG at the end of Foundation stage but subsequently reach ‘Expected standard’ at the end of KS1>national | Training completed. Job advert for Sept17- but changed to Y3/4 focus due to current cohorts in school- but will be using approaches of a KS1 pitch. | Termly pupil data |
| Teaching & Learning To further develop curriculum focussed Interventions for Maths across KS2 | July’17 Give guaranteed regular release time after tests to swiftly analyse gaps in Maths (Y5,4 and 3) & produce a brief analysis to shape teaching & esp interventions next term. Focus will be around number topics. For Sept’17 Trial making some intervention groups more flexible, curriculum area focussed and time limited. Half-termly in Maths- Y6, Y5 and Y4 | 2 x pm release time (SC/CD) KA/CD/SC/JH/MG | AP AP | Standards SC | Rigorous analysis of gaps in learning from test data- both at end of KS2 SATS and in termly ‘Assertive Mentoring’ tests leads to (i) curriculum review (ii) specific small group time-limited intervention | Year 5 done. Year 6 from RAISE online when available. Pupil Progress meetings in Sept. will reflect this approach across KS2. | Termly pupil data Gaps analysis PP meetings notes |
| Curriculum To further develop outstanding provision in computing (building on SIDP 16/17) | By end of summer term Conduct a 5 year plan w/ ICT JComtech & then RC re: hardware requirements By July’17- review ICT provision within curriculum and update planning as required Feedback from Computing curriculum training (BC 21.4.17) By June’17 Parent information re: using Purple Mash at home |  | BC BC BC | Standards SubComm RC | Technology is reliably supporting and extending learning across the curriculum. Teacher subject knowledge is highly secure. Pupil voice is highly positive. Home learning in ICT supports and extends tasks in school. | Done. Discussed at Stabdards SC and decided resourcing priorities: 1 Touchscreens 2 More chromebooks to replace laptops as they fail 3 Expand internet coverage (hall)-done Progress also made on new home-school ICT agreements and informing parents through ‘café’ mornings – w/b July10- then given home access to all platforms Significant progress in school on using Google Drive and Purple Mash resources. BC to review e-safety curriculum provision next term | 5 year plan Standards SC minutes Computing Cafes feedback and pictures Purple Mash letters Childrens’ work |
| Foundation Subjects To further develop high quality outcomes and assessment in foundation subjects | By June’17 Discuss rationale of skills progression and showcase approach. Discuss also avoiding problems caused by ‘blocking’ Subject leaders to draft skills progression charts (one side of A4) in History, Geography and Science at least. Follow up staff meeting to review drafts as a staff team. | HT will lead staff meeting HT will release subject leaders to draft skills progression (1xpm) | AP AP/HB All | Standards SC TN/RH | Termly whole school data report sheets are highly accurate for foundation subjects. There are high quality outcomes. Teaching sequences and curriculum provision in foundation subjects are informed by assessment | Done. Agreed to trial a skills progression sheet in forn t of exercise books- and look at different ways of capturing showcase of best work. Hist & Sci next term. | Science and History skills progression sheets Curriculum planning |

Gantt Chart- Summer Term 2017

Tasks

| w/b | 17.4.17 | 24.4.17 | 1.5.17 | 8.5.17 | 15.5.17 | 22.5.17 | Half-term | 5.6.17 | 12.6.17 | 19.6.17 | 26.6.17 | 3.7.17 | 10.7.17 | 17.7.17 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Whole School cycles: | Curriculum maps | Pupil Progress meetings SEND/PP reviews |  | KS2 SATS | Advertise for TA post | Attendance analysis-1 Send out Purple Mash log ins to parents? Science Week |  | Pupil Voice survey | TA PM review meetings & skills audits |  | Teacher Interim Appraisal Meetings | Assessment week Attendance analysis-2 | Termly Pupil Achievement Data Release time for gaps analysis | SEND/PP reviews TAP review |
| Staff Meetings |  | TAP | RC-ICT Training #2 | Computing Curriculum (BC- lead) From training 21.4.17 | Cluster Writing Moderation | Foundation Subjects -Skills progression - Showcase idea (AP) |  | EEF meeting | Collaborative Learning (AP) | Blue Square SEND (SC) | Release for report writing | SEND Review Curriculum Planning | English- spelling (KL) Maths- calculations policy (SC) |  |

tba

JC Comtech meeting