Termly Action Plan (TAP)- Spring Term 2019 (January-March 2019)

(Key actions drawn from SIDP & shared with staff. Governors included in termly planning, monitoring and review meetings.)

| Priority: | Key Objective: | Success Criteria: | Ofsted Area: | Links to School Vision: |
| --- | --- | --- | --- | --- |
| 1 | KS1 English To quickly close emerging attainment gaps in Reception and Key Stage 1 for children with lower Literacy ability | - To increase % of children who reach expected standard at the end of KS1 in reading and writing > national - To reduce % of children who are working below ‘Working Towards’ level at the end of KS1 in reading and writing < national | Outcomes for pupils | Love of learning Skills for life |
| 2 | High level Behaviours To improve the capacity of the school to successfully manage high level behaviours | - Staff voice indicates a high level of understanding and confidence of strategies to successfully manage children with high level behaviours | Personal development, behaviour and welfare | Skills for life Perseverance |
| 3 | STEM curriculum To develop outstanding provision in STEM subjects | - STEM curriculum across whole school meets Ofsted criteria description for outstanding - Pupil voice and subject surveys indicate a high level of pupil knowledge and enthusiasm for STEM subjects | Outcomes for pupils Quality of teaching, learning and assessment Early Years Provision | Love of learning Skills for life |
| 4 | Foundation subjects To further develop skills teaching in curriculum foundation subjects | - Skills progression planning is embedded across foundation subjects - Assessment information is used to inform teaching and learning across the school, and between age groups. | Outcomes for pupils Quality of teaching, learning and assessment | Love of learning Skills for life |
| 5 | Safeguarding To further strengthen safeguarding provision in the school | - Safeguarding arrangements reflect best practice in all areas. | Personal development, behaviour and welfare Quality of leadership and management | Skills for life |
| 6 | Middle leadership-core To use subject audit recommendations to further raise attainment in core subjects and Early Years | - End of key stage progress measures in core subjects and EYFS are > national. - Subject leaders are actively developing provision in each subject | Outcomes for pupils Quality of teaching, learning and assessment Early Years Provision | Love of learning Skills for life Make it your best Persevere |

| Target: | Input, activities & tasks (Including key ‘milestones’) | Resources | Person | Monitoring | Success Criteria | Updates Apr’19 |
| --- | --- | --- | --- | --- | --- | --- |
| KS1 English To quickly close emerging attainment gaps in Reception and Key Stage 1 for children with lower Literacy ability | Purchase ELKLAN practical resources AND/OR ICAN resources eg https://elklantraining.worldsecuresystems.com/resources/early-language-builders (for easy incorporation into the classroom) Purchase peripatetic support for children in Owlets for S&L. through ‘Communicate’ (peripatetic) S&L training for Early years-BC (14.3.19 & 18.3.19) & all staff through ‘Communicate’ (peripatetic) Staff meeting British Dyslexia Association resources Organise a KOW visit for spring term to develop enrichment- linked to ‘Homes’ topic. Organise some visits around village to look at KOW (see above) New spelling approach at KS1 trialled and extended to Y1 children. Review system at end of term. Parent involvement with spelling KS1/2 and a WS spelling event to be organised for Spring term. | S&L resources £500+ EHCP assessment | AP/BC AP BC KL KL | Standards SC- half-termly meetings and/or monitoring visits | Progress of children in Rec/KS1 identified with low literacy and/or speech and language issues is good. Spelling of high frequency words at the end of key stage 1 is as good as the other elements in the end of key stage writing assessments. Early years children have additional opportunities to use vocabulary related to real world around them. | Bespoke ‘Communicate’ package purchased for Summer term – includes upskilling of staff and is sustainable. EYFS & KS1 staff have attended ECSH courses & TA’s booked for next one in summer term. TA’s have also visited parallel classes in other schools. Resource purchase planned through EYFS audit. Y1 are now using revised spelling approach. Event tba. |
| High level Behaviours To improve the capacity of the school to successfully manage high level behaviours | Review and update Touch policy with reference to Early Years. Behaviour and Touch policies on school website Review of Home School Agreement | Staff meeting time for discussion | AP/BC Standards SC | Standards SC- half-termly meetings and/or monitoring visits | Touch policy is clear and supports staff across school. Behaviour policy is well understood and promotes consistency across school. | All actions completed. |
| STEM curriculum To develop outstanding provision in STEM subjects | Science WS STEM days set for whole year (4.3.19)- consider linking to WS Big Writing as a follow up task – plan as part of termly staff meeting linked to science assessments Coding club & Robot club 2nd half term for Y3-4 and 5-6 Extend library scanner to Y3/4 –purchase new PC if required Introduce a PC/monitor into Owlets | Staff meeting time for discussion ASC time £250 | AP/HB AP AP/SC AP/BC | Standards SC- half-termly meetings and/or monitoring visits | STEM remains a focus for school. Children are able to demonstrate good levels of STEM skills and an independent self-confident approach to new challenges. Many children have experienced coding in different contexts inc Scratch and Sphero robots. Owlet children have good curriculum access to resources. | WS STEM day was successful. Both coding club and robot clubs also good- team entered for UEA scratch off. Y5 team also entered in Jaguar F1 challenge – sponsorship bids successful. |
| Foundation subjects To further develop skills teaching in curriculum foundation subjects | Create a rolling 3 year plan for foundation subject reviews- linked to training budget and resource procurement. Visit for staff to local resident forest area offer- Forest schools now RA completed Outdoor learning resource share staff meeting eg https://www.woodlandtrust.org.uk Plan a ws day for summer term? Somerset Outdoor Learning Academy Work towards NOLA Award (free recognition) Consolidate timetabled outdoor learning sessions KS1- training? Visits? Shared staff meetings with Blofield/Wicklewood-6.3.19 Focus: subject leadership in foundation subjects | Rainbow Continuum to support curriculum planning for 2018-19 Staff meeting time Subject leader time | All staff HB AP AP/CD | Standards SC- half-termly meetings and/or monitoring visits | Curriculum maps updated HQPE award achieved. Forest resource used to further enrich curriculum. Teachers are benefitting from sharing best practice in other schools. Sports Premium spend has been reviewed and a plan written for this academic year. | Changed focus to planning for new Ofsted curriculum expectations- see SIDP 2019-20 |
| Safeguarding To further strengthen safeguarding provision in the school | Migrate training records to new spreadsheet Staff Meetings short standing items to raise awareness- SCR’s general updates DSL training-JH (30.1.19 & 31.1.19) Online safety policy review Staff meeting- feedback on restorative approach (SC) Preparation work for statutory SRE- Cluster joint approach to RSE agreed- resources and training purchased. Mental Health & Wellbeing- results of audit>draft an action plan (for summer 2019 implementation) | Office time to migrate records Staff meeting time as indicated Staff meeting time £300 training costs £500 resources | SC AP AP/MA | Standards SC- half-termly meetings and/or monitoring visits | FSP training refreshed. Staff knowledge remains high. New spreadsheet in operation. SRE preparatory work has been completed. | All actions completed- some subsumed into SIDP 2019-20. |
| Middle leadership-core To use subject audit recommendations to further raise attainment in core subjects and Early Years | Maths- Pupils modelling calculation methods for school website- SC English- Nessy Introduce a suitable writing intervention at KS1. Spelling (see above) SEND- update SEND provision map & use of revised proforma Allocate Ed Psych visits Review use of dyslexia subscription and allocate initial viiits | Staff meeting time £200 EYFS resources SC supply afternoon for Maths videos | SC HB BC KL AP BC SC | Standards SC- half-termly meetings and/or monitoring visits | PSQM award achieved. Staff knowledge of bar modelling increased Nessy introduced for selected children EYFS resources refreshed and being used SEND map updated to reflect current practice. | Updated SEND provision map & use of revised proforma Allocate Ed Psych visits Allocated initial visits Cluster SEND group to work in peers to evaluate each others provision in summer term- see cluster SEND minutes |

Gantt Chart- Spring Term 2019

| w/b | 3.1.19 | 7.1.19 | 14.1.19 | 21.1.19 | 28.1.19 | 4.2.19 | 11.2.19 | HT | 25.2.19 | 4.3.19 | 11.3.19 | 18.3.19 | 25.3.19 | 1.4.19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Whole School Cycles | TAP draft | WS data SEF update Attendance2 | 18.1.19 VNET curriculum (Clubs: Y3/4 robots) | 24.1.19 Standards SC 30.1.19 DPO visit | 1.2.19 Cluster Heads- inc dates for moderations | Attendance 3 5.2.19 FGM | 15.2.19 Resources Safeguarding paperwork- records migration |  | (Clubs: Y5/6 Scratch) | Preparation for subject audits | Attendance 4 | T&L evaluations with VNET Ann Keen (Thus 21.3.19) | 27.3.19 Cluster Heads Assessment week | WS data review TAP draft |
| Staff Meetings | Inset- Pupil Progress meetings Dyslexia training (TAs) GDPR training (Ts & office) | UEA visits Touch policy-BC Science assessment- HB/AP | SEND G&T TAP draft | Planning for next WS Science day TAP finalise | Foundation subjects Science assessments | Mental Health & Wellbeing development plan Feedback from VNET curriculum conference Nessy for IPADS | British Dyslexia Association Resources |  | Outdoor learning resources online & discussion NOLA award | WED 6.3.19 Blofield | Subject audits | SIDP 2019-20 Discussion (inc RSE) |  |  |

TBA

Maths modelling for website

Parental spelling event-KS1